## Summary data (hidden)
Summary Dashboard
Apr | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | Last 24 Hours
Phases
MOE | COVID Cases Onboard |  |  |  |  | Demand / Capacity |  |  |  | Media Trend | [5 empty] | Public Perception Trend
| ROM |  | Isolation
[6 empty] | 0 / 1000 | [9 empty] | 0 / 1000
MOP | Admissions | [6 empty] | Inpatient Status | [6 empty] | Surgeries | [6 empty] | Next 24 Hours
| xx | ICU Admissions | [5 empty] | xx | Total Census | [5 empty] | xx | Total surgeries performed
| xx | Ward Admissions | [5 empty] | xx | ICU Patients (XX/XXX Vented) | [5 empty] | xx | Sub specialty Surg Cases
| xx | Surgery Admissions | [5 empty] | xx | Ward Patients | [5 empty] | xx | Sub specialty Surg Cases
| xx | Intermediate Care Admissions | [6 empty] | (XX Lower Bed / XX Upper Bed) | [5 empty] | xx | Sub specialty Surg Cases
| xx | Limited Care Admissions | [5 empty] | xx | RRT/Code Blues Executed | [5 empty] | xx | Sub specialty Surg Cases | [5 empty] | Future Operations
[15 empty] | xx | Sub specialty Surg Cases
[15 empty] | xx | Total Surgeries for mission
| Discharges/Transfers/Deaths | [6 empty] | Critical Equip/Blood | [6 empty] | AMAL Overall %
| xx | Discharge to home | [5 empty] | x of xx | Ventilators | [5 empty] | xx | OR AMAL % | [5 empty] | Decision Needed by PG/Gov
| xx | Transferred to alternate hospital | [5 empty] | x of xx | Dialysis Machines | [5 empty] | xx | ICU AMAL %
| xx | Transfer to SNIF | [6 empty] | BIOFIRE Status | [5 empty] | xx | Ward AMAL %
| xx | Deaths | [5 empty] | X of xx | pRBC | [5 empty] | xx | LAB AMAL %
| xx | Total D/T/D for mission | [5 empty] | X of xx | Platlets
[8 empty] | X of xx | FFP/Cryo
P-team Priorities | [6 empty] | Risk | [6 empty] | Cross Coordination | [7 empty] | Strategic Communications

## Initiative Tracker
Protocols Initiative Tracker
| # | Initiative Name | Expert/SMEs | State's Role | Initiative Owner | Prioritization | Status | Title of the Document | Interdependencies with other P-teams | Escalations/Approvals/Decisions
| 1 | Decision criteria and plans to address major outbreaks in residential facilities | Expert/SMEs: Kate Massey & Dr. McFadden | 2 - State issues guidance | Nicole Hudson | High | On track | Regional Hub Guidance | With Nursing Home EO | At the CHECC for Review
| 4 | Model for Hotel Isolation | Expert/SMEs: Dr. Fales, Lyndsay Tyler, Sarah Esty | 4 - Direct state implementation | Sarah Etsy | Medium | On track
| 6 | Protocol for Medical Rationing that Include Non-Discrimination Protections | Leslie Asman |  | Nicole Hudson | High | On track |  |  | Several outstanding questions posed by Leslie to Leadership
| 7 | Provider Memo on Disparities | Dr. Khaldun | 2 - State issues guidance | Nicole Hudson | High | Completed
| 9 | Transfer of Personnel | Director Gordon |  |  | Low
| 10 | Draft Order on the PPE and Medication Transfers | Dr. Fales | 3 - Executive order | Director Gordon | Medium | Completed |  |  | Draft EO included to Director Gordon on 4/29
| 11 | Executive Directive on Race and Ethnicity Data | Dr. Khaldun | 3 - Executive order | Dr. Khaldun | High | On track
| 12 | Scenario/Criteria for Isolation Orders | Dr. Khaldun |  | Dr. Khaldun | Medium
| 13 | Workforce allocation |  |  |  | Medium
| 14 | Opening up |  |  |  | Medium |  |  |  | Action needed: Raz to share publications
| 15 | Testing allocation and guidance |  |  |  | Medium
| 17 | Product approvals: next best alternatives |  |  |  | Medium
| 17 | PPE conservation | Director Gordon |  |  | Medium
| 18 | Hospital staffing ratios |  |  |  | Low
| 19 | Hospital surge capacity guidance |  |  |  | Low
| 20 | Non Discrimination Principles
| 21 | Cultural Competence | Brenda Jegede | 2 - State issues guidance | James Bell | Medium | Completed
| 22 | Testing Approach and Strategy | Andie Taverna/Dr. Khaldun | 2 - State issues guidance | Andie Taverna | High | On track
| 23 | Behavoral Health Hospital Transfer | Dr. Pinals |  | Nicole Hudson | High | Attention needed |  |  | SME review and comment needed
| 24 | Behavoral Health Expanding Access (telehealth, etc) | Dr. Pinals/Allen Jansen |  | Nicole Hudson | High
| 25 | Elective Procedures FAQ Hospitals | Dr. Khaldun/Dr. McFadden | 2 - State issues guidance | James Bell | Low | Not pursuing/Cancelled |  |  | Dr. Khaldun reviewing to inform document for Governor's Office
| 26 | Elective Procedures FAQ General Public | Dr. Khaldun/Dr. McFadden | 2 - State issues guidance | James Bell | Medium | Not pursuing/Cancelled
| 27 | Race/Ethnicity Reporting Requirements | Jim Collins/Sarah Lyon Callo | 2 - State issues guidance | James Bell | High | On hold |  |  | Multiple projects taking place to determine feasibility.
| 28 | Guidance on Reinforcing the Ability to Receive Emergency Treatment |  |  |  | High
| 29 | Reprioritizing PPE for Nursing Homes | [7 empty] | To begin with Erin McGovern
| 30 | Nursing home mask requirements/ all congregate care settings - Linked to Policy | [7 empty] | Director Gordon to follow up with Mark
| 31 | N95 Mask Conservation System | Director Gordon |  | Nicole Hudson | High
x | x | x | x | x | x | x | x | x |  | x

## Action Tracker
Protocols Action Tracker
| Check-in meeting | [7 empty] | Status Update from last meeting
| Date | Priority | Initiative Name | Action | Action Owner | Due date | Support needed to complete | Roadblocks to completion | Status | Pending Actions to Complete
| 2020-04-13 | High | Protocol for Medical Rationing that Include Non-Discrimination Protections | Leslie escalated key questions to leadership | Director Gordon | 2020-04-13 | Director Gordon to review and send thoughts to Dr. J |  | Completed | At EOG
| 2020-04-13 | High | Provider Memo on Disparities | Nicole drafting; draft to Dr. J by EOD | Nicole Hudson | 2020-04-13 | Dr. J to review final version |  | Completed | Finalizing draft for distribution on 4/20
| 2020-04-13 | Medium | Hotel Isolation | Discuss with Sarah: target populations and expanding to include those who need to self-isolate but cannot safely follow protocols at home, EOG briefing | Dr. J/Director Gordon | 2020-04-13 |  |  | In progress | Document is on track
| 2020-04-16 | Medium | Cultural Competence Guidance | Draft guidance for Providers related to Cultural Competence and practice | James Bell | 2020-04-18 |  |  | Completed
| 2020-04-16 | Low | Draft Order on the PPE and Medication Transfers | Dr. Fales is drafting initial order | Director Gordon | 2020-04-30
| 2020-04-16 | High | Elective Procedure FAQ Hospital | James to request guidance/FAQ from Linda Scott, Dr. McFadden | James Bell | 2020-04-20 | Dr. Khaldun has initial draft |  | In progress | Cancelled.
| 2020-04-16 | Low | Elective Procedure FAQ General Public | James to request guidance/FAQ from Linda Scott, Dr. McFadden | James Bell | 2020-04-20 | Spoke with Linda Scott, she will be getting assistance from MHA and other SMEs. |  | Completed | Holding guidance for now
| 2020-04-16 | Medium | Behavioral Health | Scheduling a meeting with Dr. Pinals and others related to BH guidance docs | Nicole Hudson | TBD | Dr. Pinals sent draft to senior leadership for review. Comments due by 4/20 12:00pm |  | In progress | Review is needed before document can move forward
| 2020-04-17 | Medium | Reporting by Race/Ethnicity | Drafting memo for race/ethnicity reporting requirements and implementation implications | James Bell | 2020-04-18 | Sarah Lyon Callo is reviewing the initial draft. Dr. Khaldun to follow up with Illinois |  | In progress | At this time, no EO is necessary. Evaluating feasibility studies.
| x | x | x | x | x | x | x | x | x | x

## 5pm Meeting Input
Protocols Update
Mark all items that need to be brought to leadership attention as "Escalate" in Column 2 for each section
| P-team Summary | P-Team Priorities |  |  |  | Metric 1 |  |  | Metric 2
|  | 1 | On track | Decision criteria and plans to address major outbreaks in residential facilities (Regional Hub Guidance)
|  | 2 | On track | Protocol for Medical Rationing that Include Non-Discrimination Protections |  | (TBD) |  |  | (TBD)
|  | 3 | On track | Behavioral Health Guidance on Hospital Transfers
|  | 4 | On track | N95 Mask Conservation
|  | 5 | On track | Race/Ethnicity Reporting Requirements
| Actions and Decisions | Last 24 Hours |  |  | Next 24 Hours |  |  | Future operations (Next 72-96 hours)
|  | 1 | On track | Regional Hub Guidance sent to the CHECC for final review | 1 | On track | Begin drafting the newly added guidance documents | 1 | On track | Release Regional Hub Guidance
|  | 2 | On track | PPE Conservation discussion and research underway (state level view and hospital level view) | 2 | On track | Finalize Regional Hub Guidance sent to the CHECC for final review | 2 | On track
|  | 3 | On track | Drafting order on PPE and Medication Transfer | 3 | On track | Follow up with Sarah LyonCallo re: race reporting needs | 3 | On track
|  | 4 | On track |  | 4 | On track | PPE Prioritization for Nursing Homes | 4 | On track
|  | 5 | On track |  | 5 | On track |  | 5 | On track
| Risks and Inter-dependencies | Risks and general concerns |  |  | Interdependencies with other P-groups |  |  | Updates or action items for the Governor
|  | 1 | On track |  | 1 | On track | Nursing facility guidance/FAQs developed based on the EO | 1 | On track | Protocol for Medical Rationing that Include Non-Discrimination Protections - with EOG for review
|  | 2 | On track |  | 2 | On track |  | 2
|  | 3 |  |  | 3 |  |  | 3
|  | 4 |  |  | 4 |  |  | 4
|  | 5 |  |  | 5 |  |  | 5

## Hidden_Back-up (hidden)
People | Yes | Idea | On track | Not started | High | On track | 0 - no involvement
Places | No | Mentioned - to confirm | Facing some issues | In progress | Medium | Escalate | 1 - MHA led guidance
Product |  | In-Flight | Attention needed | Completed | Low | Include for Gov | 2 - State issues guidance
Protocol |  |  | On hold |  |  |  | 3 - Executive order
Policy |  |  | Not pursuing/Cancelled |  |  |  | 4 - Direct state implementation
Pecunia |  |  | Completed
Data