## Open Action Items
Action Item Register MDHHS COVID-19 Public Health Administration/SIA
Item | Project | Description | Next Steps | Owner | Open Date | Due Date | Dependencies | Status
Validate priority of COVID-19 work | PHA COVID-19 Strategy | PHA & SIA team to align on priority of all COVID-19 Transition work to take place | Meeting scheduled to review proposed SIA priority with Jean on 09/17/20. Work priority and next steps aligned with Jean. Next steps are to meet with each group to better understand path forward. Meetings scheduled for: Contact Tracing: Meeting with Jonathan Warsh, Rachel Zuckerman and Katie Macomber for 9/29. Isolation: Meeting with Sarah Esty scheduled for 9/28. Communications: COVID-19 Support Review Meeting 10/6. | All | 2020-09-14 | 2020-10-06 |  | In progress
PHA Testing & Collection Org Chart Finalization | Testing Unit Team | Finalize the testing team org chart with all vacancies filled and team structure aligned on. |  | All | 2020-09-14 | 2020-10-06 |  | In progress
Overall PHA COVID-19 Org Chart | PHA COVID-19 Strategy | Finalize the overall COVID-19 org chart with all vacancies filled and team structure aligned on. |  | All | 2020-09-14 | TBD |  | In progress
Communications: Announcement of Jason's transition | Testing Unit Team | Amy Allen to work with PHA and SIA team to formalize the announcement of Jason's transition into the COVID-19 Testing Coordination Director role | Amy to coordinate with PHA/SIA team to formalize announcement | Amy Allen | 2020-09-14 | 2020-10-02 |  | In progress
PHA Covid-19 Overall Transition Plan | PHA COVID-19 Strategy | SIA team to develop comprehensive transition strategy plan for PHA (similar to what Amber Harger developed with the 211/Public contact center transition) and review/formalize with Jean | In progress. | Cassandra Secrest, Steve Schreier. Danielle Lefere, Ken Young | 2020-10-06 | TBD |  | Not Started
School Surveillance/Testing Project Manager Position | PHA COVID-19 Strategy | School Surveillance/Testing Project Manager Position i. Where will this position reside? ii. Is this position an FTE? iii. Need for additional liaison on testing unit team? | TBD-discuss during our 9/28 PHA/SIA meeting | Jason Wilkinson | 2020-09-28 | TBD |  | Not Started
Vulnerable Population #2 Position Vacancy | Testing Unit Team | Currently there is a gap for this position. There may be a possible CDC candidate to fill this role | Jason to contact Lynn and her supervisor and review | Jason Wilkinson | 2020-09-14 | TBD |  | In progress
Equipment Outfitting for new staff | PHA COVID-19 Strategy |  | Status? | Michele Borgialli | 2020-09-14 | TBD |  | In progress
MPHI Contract Process | PHA COVID-19 Strategy | Verify process of transitioning contracts with MPHI. What process do we need to adhere to transition current contracts into new positions (specifically Louis Albrant & Norm Hess) | Michele to follow-up with MPHI | Michele Borgialli, Danielle Lefere | 2020-09-14 | 2020-10-02 |  | In progress
Testing Liaison Support Team | Testing Unit Team | Steve to contact Aisha and Natalie's managers to see about staying on to support. | Status? | Steve Schreier | 2020-09-14 | 2020-10-02 |  | In progress
Local Health Department Liaison Role | Testing Unit Team | Aarti Dave. Meeting scheduled to review position requirements and begin transition schedule. | Aarti Dave. Meeting scheduled to review position requirements and begin transition schedule. | Steve Schreier | 2020-09-14 | 2020-10-02 |  | In progress

## Completed Action Items
Action Item Register MDHHS COVID-19 Public Health Administration/SIA
Item | Project | Description | Owner | Open Date | Due Date | Dependencies | Status
PHA/SIA Weekly Touchpoint Agenda | PHA COVID-19 Strategy | Create a standing agenda for our weekly touchpoint meetings. We will include this action item register as an agenda topic. | Cassandra Secrest | 2020-09-14 | 2020-09-18 |  | Complete
Private & Community Based Testing Liaison Role merge | Testing Unit Team | Verify with Katie and Kathleen that Norm Hess will take ownership of both the public and private sector roles, which will merge into one testing liaison role. Additionally, the MPHI contract will need to be updated. | Steve Schreier | 2020-09-14 | 2020-09-18 |  | Complete
Artie Dave Transition to Testing team | Testing Unit Team | Once PD is developed for Lab Testing Liaison, follow-up with Artie Dave to review potential fit for her to transition into that role | Danielle Lefere | 2020-09-14 | 2020-09-18 |  | Complete
Vulnerable Population #1 Position Description (PD) | Testing Unit Team | Finalize PD for Vulnerable Population Testing Liaison | Danielle Lefere | 2020-09-14 | 2020-09-18 |  | Complete
Lab Capacity Liaison Position Description (PD) | Testing Unit Team | Create and finalize PD for Lab Capacity & Testing Liaison | Danielle Lefere | 2020-09-14 | 2020-09-18 |  | Complete