Transition Management Plan (Functional)

COVID-19 statewide testing unit

# 1. Overall Transition Objective Statement

The Transition model is structured to minimize business service level inefficiencies during the transition of the current COVID-19 Public Response activities for the Statewide Testing Unit working under the direction of the Michigan Department of Health & Human Services [MDHHS] Public Health Administration [PHA] which includes a structured training methodology to speedily transition key business processes.

# 2. Transition Management Plan Overview (Model, Objectives, Approach, and Structure)

The Transition Plan is based on a proven model that is structured to minimize business service level inefficiencies during the transition of the COVID-19 Public Response activities to support a long-term working solution, while simultaneously optimizing on the benefits of moving to a more standard Testing Unit Coordination environment with proven best practices in place. This model utilizes a structured training methodology to ensure efficient joint understanding and modification of existing processes, prior to the full transition of key knowledge and business processes of the current processes to new solutions.

Key to the success of this transition will be the collaborative re-engineering and migration of current processes, knowledge, and practices to ensure that we are leveraging the benefits of integrating them into a more standard, future steady-state structure. A ‘Reengineer and Migrate’ transition project can be very intricate because it includes resources from multiple areas and departments; it requires extensive partnering, and often there is significant emotion involved. For these reasons, a shared vision and strategy will need to be developed early on and remain in all participants line-of-sight.

By leveraging best practices from previous transitions, combined with an existing relationship between the PHA, the overall goal of this model is to enable more time to be spent on critical transition planning and execution to ensure collaboration and a shared vision early and revisiting frequently.

## Transition Management Plan Objectives:

The objectives of this Transition Management Plan are to:

- Define and plan resources for the transition clearly identifying the activities, timelines, roles and responsibilities, and monitor the engagement on an ongoing basis

- Detailing of process, technology and infrastructure (‘As Is' and ‘To Be') and actual transition

- Verify operational design of specific processes identified to be suitable for process delivery

## Transition Management Plan Approach (4 Key Steps)

The Transition Management approach is a four-step transition process, whereby each step has defined result, as follows:

- Project Planning (Step 1) results in a Project Plan Document

- Process Definition (Step 2) results in a Process Document

- Transition Planning (Step 3) results in the Initiation of a Pilot Process

- Design Verification (Step 4) leads to the Full Rollout Process

The above four-step transition process best supports the ‘Re-engineer and Migrate’ approach, which is useful when the process requires standardization, will benefit from a more standard and proven structure, or is due to undergo significant change in the near future (systems change or process change).

## Transition Management Structure

This plan is structured around completion of the four previously defined process steps, whereby the transition’s entirety is built based on completing each of the activities defined within each of process inclusion areas elements.

### Transition Management Matrix: Per Process SteP Results and Processes Break-Down (High Level Overview)

# 3. Project Planning

The Project planning phase is necessary to evaluate the complexity of the tasks lying ahead. In this phase we form a team to accomplish the project. Additionally, we begin to consider the number of processes that will need to be migrated.

Project Planning consist of the following with the outcome being a full Project Plan document:

| Process Step | Process Inclusion Area | Process Area Break-Down Elements |
| --- | --- | --- |
| STEP 1: Project Planning | - Project team set-up | - Team Selection and Stakeholders - Roles and Responsibilities Defined - Project Briefing |
|  | - Dates defined | - Identify key Activities - Define internal/ external sign-offs for activities - Develop timeline and Gantt chart - Internal sign-off (Timelines) |
|  | - Communication plan established | - Information flow within project team - Information flow with vendor - Escalation mechanism - Review Mechanism |
|  | - Resource requirement checklists defined | - Process - Hiring - Training - IT / Telecom - Facility - Quality - Legal |

## Project Planning: Project Team Set Up

The project team will consist of a wide-range of individuals from various cross-functional teams.

### Stakeholders & Testing Unit Team

| COVID-19 RESPONSE TRANSITION STAKEHOLDERS & TEAM MEMBERS |  |  |
| --- | --- | --- |
| Team Member | Role | Work Area/Activity |
| Jean Ingersoll | MDHHS Business Owner (PHA) | All |
| Jason Wilkinson | COVID-19 Testing Coordination Director | Statewide COVID Testing |
| Aarti Dave | Lab Capacity Liaison | Statewide COVID Testing |
| Louis Albrant | Data Architect | Statewide COVID Testing |
| TBD | Data Specialist | Statewide COVID Testing |
| Norm Hess | Community & Private Sector Testing Coordination Lead | Statewide COVID Testing |
| TBD | Community & Private Sector Testing Coordination Support Staff | Statewide COVID Testing |
| TBD | Vulnerable Population Liaison #1 | Statewide COVID Testing |
| TBD | Vulnerable Population Liaison #2 | Statewide COVID Testing |
| TBD | Local Health Department Liaison | Statewide COVID Testing |
| TBD | Education Liaison | Statewide COVID Testing |
| TBD | Central Scheduling | Statewide COVID Testing |

COVID-19 Response History:

| ## Past PHA COVID-19 Response Activities | Activity Date |
| --- | --- |
| Press release on cases under investigation | ## 1/24/20 |
| www.michigan.gov/coronavirus website established | ## 1/27/20 |
| MIHAN to LHDs and Tribes for CHECC activation and Update on 2019-nCoV | ## 1/31/20 |
| Established routine MDHHS internal calls | ## 02/2/20 |
| ## Super Bowl Sunday – notified by CDC that Detroit Metro Airport was a funneling airport. MDHHS internal call as well as call with City of Detroit and Wayne Co Health Departments | ## 02/3/20 |
| Initiated routine conference calls with LHD and Healthcare | ## 02/5/20 |
| EMS Emergency Protocol for Destination and Transport of Pts at Risk for Novel Coronavirus distributed | ## 02/6/20 |
| First delivery of PPE from SNS | ## 2/12/20 |
| EMResource reporting for hospitals initiated | ## 2/14/20 |
| BOL initiates lab testing | ## 2/28/20 |
| SEOC activated | 2/28/20 |
| Dr. Khaldun Clinician Webinar | 03/5/20 |
| Outreach to Medical Examiner Community | 3/10/20 |
| Governor declares State of Emergency | 3/10/20 |
| Presumptive cases identified | 3/11/20 |
| Dedicated call for SNF | 3/19/20 |
| Dedicated calls for EMS initiated | 3/31/20 |
| Activation of MIMORT to central storage location | 4/25/20 |

## Project Planning: High Level Dates Defined

This section will identify and call out key dates and activities required to develop an initial timeline for the Transition of COVID-19 Testing Unit activities. This section will also facilitate the alignment of activities based on any dependencies.

### Identify key Activities

Overall Dates Defined

| ## Current & Future PHA COVID-19 Testing Unit Activities | Planned Finish Date |
| --- | --- |
| ## Fill remaining position gaps for COVI-19 Testing Unit Team | ## 10/09/20 |
| ## McKinsey-Remaining process documentation | ## 10/08/20 |

### Information flow within project team

To enhance information flow and promote consistent project team communications the following are in place and have been agreed on (Please populate as needed for your team):

- Reoccurring Touch-Point Meetings

  - Meeting Details

    - Standing Agenda Order will be as follows:

- A Microsoft Teams Channel should be established for the team to communication via tagging individuals to get their attention.

- A SharePoint Site should be utilized to store all Transition Documentation and is located at:

- A Weekly Status Report if needed.

### Required Communications (Internal/Current Employees and their Managers)

The following communications will need to be coordinated, approved and delivered according to schedule:

| Communications Message Objectives: (Content) | Delivery To/Audience(s): (CC Managers of All Individuals) | Planned Delivery Date: |
| --- | --- | --- |
| TO: REASON: |  |  |

### Escalation mechanism

### Review Mechanism

## Project PLANNING: Sign-Off Authority Established

### Identify customer interface

### Define sign-off mechanism

# 5. Transition Planning

The plan encompasses the names of the participants and also a deadline for all the activities. The project team charts out a technology assessment plan with all relevant details, besides developing a business continuity plan. The stakeholders must sign off on all plans.

Transition Planning consist of the following with the outcome being the Initiation Pilot Process:

| Process Step | Process Inclusion Area | Process Area Break-Down Elements |
| --- | --- | --- |
| STEP 3: Transition Planning | - Site readiness gap analysis | - Identify gaps - Define action plans/ time frame |
|  | - Risk mitigation plan | - Identify & classify potential risks - Risk effect analysis - Define Mitigation measures |
|  | - Detailing MIS / Reporting requirements | - Review existing MIS/ reports - Define & Finalize report formats - Identify data sources - Define MIS formats, data sources, frequency, responsibilities, and recipients |
|  | - Internal sign-offs | - Communicate Transition Plan to internal customers - Discuss, resolve & obtain sign-offs' |
|  | - Finalize transition document / Customer sign-off | - Develop Transition Document - Communicate & discuss with customer - Update document - Obtain customer sign off |