## Format
Domain:
Objective
Activity
Lead
Milestone
Milestone Date
Cross reactivity

## Plan
THINK ABOUT SURVEILLANCE AS COLLECTION (PROTOCOL AND SYSTEMS), ANALYSIS, DISTRIBUTION AND INTERPRETATION - INCLUDE MEETING THINKING
DOMAIN | OBJECTIVE | ACTIVITY |  | Lead | Status | 48 Hour Plan | Weekly update
Surveillance: Develop and disseminate reliable estimates of COVID-19 spread
| Data Collection: Maintain Michigan Disease Surveillance System, Michigan Syndromic Surveillance System, Testing Analysis projects |  |  | Jim Collins
|  | Activity | Daily data pull
Sentinel Surveillance: Develop sentinel surveillance systems that are not influenced by limitations in testing capacity
|  | Activity | Enhancement of Influenza Hospitalization Surveillance Project | Sue Kim | Ongoing
|  | Activity | Incorporate COVID testing into FluNet, representative sample of outpatient practices | Michelle Doebler/Justin Henderson
|  | Activity | Enhance FluNet through collaboration with UMICH ILI NETWORK | Sue Kim
|  | Activity | Enhancement of Michigan Sentinel Influenza Laboratory Network | Sally Bidol | Ongoing
|  | Activity | Development of symptom system with academic partner | Sarah Lyon-Callo | Ongoing: DUA, LOA in place
Demographic: Improve availablity of statistics for demographic populations, including race/ethnicity, veterans status, disability status
|  | Activity | Match test records with MHIN data to improve race and ethnicity - pilot | Ed Hartwick | Pilot Completed - less than 50 percent of records had race data available
|  | Activity | Match case data with Medicaid claims to obtain inofmraiotnon disability status, race and ethnicity, veterans status | Patricia McKane | Ongoing
|  | Activity | Memo to health departments reminding them of need to collect data on race/ethnicity and other variables | Joneigh Khaldun | completed
| Protocol: Ensure common surveillance and investigation approach across public health system |  |  | Lead
|  | Activity | Aid local public health in case investigation, contact solicitation and contact tracing | Joe Coyle | Ongoing
|  | Activity | Develop guidance to local health on definitions of community spread | Jim Collins | completed
|  | Activity | Develop guidance and materials for LHD and SDOH on probable case defintions | Jim Collins | completed
Milestone
Milestone
Milestone
Milestone
Milestone
|  | Activity | Improve LHD and SDOH access to EMRs for case investigation | Sarah Lyon-Callo | HOLD
|  |  | Milestone | De la Rembyle |  |  |  | Yes
|  |  | Milestone | Lyon-Callo |  |  |  | Yes
Milestone
|  |  | Milestone | Collins/RE
|  |  | Milestone | Woodruff
|  |  | Milestone | Woodruff
Milestone
|  | Activity | Improve rapidity of collection of onset date and contacts | Joe Coyle | Ongoing
Estimates: Develop estimates on impact of COVID
|  | Activity | Recovered: Develop and publish recovered cases estimates | James Collins | Complete
Lead
Milestone
Milestone Date
|  | Activity | Cases: Develop and publish analysis of case data by date of onset | Sarah Rockhill | Complete
|  | Activity | Mortality: link addresses of SNFs, nursing homes with death certificates for COVID to identify estimate of deaths | Jeff Duncan | Ongoing
|  | Activity | Recovered: Assist in Recovery Survey by academic partner | Patricia McKane | IRB in review; Umich team in place
|  | Activity | Hospitalization: Develop and publish hospitalization estimates | Betsy Wasilevich | Data to SEOC daily, DUA for data to go to MiSafeStart Dashboard
|  | Activity | Nursing Home: Develop and publish excess mortality estimates from death certificates | Jeff Duncan | Complete
|  | Activity | Mortality: Develop and publish outbreak associated death counts | Seth | Complete
|  | Activity | Mortality: Assist Academic Partner in Conducting an COVID Mortality Review | Patricia McKane | Funding in process
SME: Provide Epidemiologic and Communicable Disease Subject Matter Expertise Support
|  | Activity | Guidance to Office of state employer on reopening | Kory Groetsch
|  | Activity | Develop public health guides for settings during reopening | Kory Groetsch
|  | Activity | ICP to LTC facility work groups | Brenda Brennan
|  | Activity | MDOC support | Jevon McFadden | Weekly support; ongoing questions
|  | Activity | Support to ITRAC in response to Congregate settings | Brenda Brennan
|  | Activity | Development of reopening guidance documents | Kory Groetsch
|  | Activity | Develop estimates of laboratory capacity | Peter Davidson with BOL | Daily update to SEOC for McKinsey
|  | Activity | Nursing Home: Technical Assistance to data collection in EMResource | Joe Coyle
| Objective | Providing data for coordination of testing resources |  | Andi Taverna | Ongoing
| Objective | Run provider hotline to coordinate BOL samples |  | Matthew Buck | Completed
| Objective | Support to Public hotline |  | Sarah Esty | Ongoing
Epidemiologic analysis: Develop indepth understanding of direction of pandemic, including modelling and subinvestigations
| Objective | Obtain modelling estimates of spread, peak, and impact of mitigation
|  | Activity | Working with modelling efforts at University of Michigan | Sarah Lyon-Callo | Ongoing
| Objective | Understand mortality and recovery |  | Patricia McKane | IRB in review; Umich team in place
|  | Activity | Assist in Recovery Survey by academic partner | Patricia McKane | IRB in review; Umich team in place
| Objective | SEROLOGY
|  | Activity | Collaborate with research partner on serologic study | Marty Soehlen
| Objective | Participate in enhanced investigation of pandemic with research and federal partners
|  | Activity | CDC Enhanced investigation of cases who have died | Patricia McKane
Lead
Milestone
Milestone Date
Cross reactivity
|  | Activity | CDC laboratory project on genomics | Marty Soehlen | Ongoing
Lead
Milestone
Milestone Date
Cross reactivity
|  | Activity | Participate in CDC Assessment of 10 cases | Shannon Johnson | Completed
|  | Activity | Participate in CDC Assessment of cases who have died | Seth Eckel
|  | Activity | Participate in CDC assessment of COVID-19 during pregnancy nd gestation | Chris Fussman
|  | Activity | Pentagon Modelling project request | Sarah Lyon-Callo | Not approved by Gov office
provide data for purposes of educating the public about COVID risk
Predictive mapping from University of Michigan (honey comb mapping)
APPLE CART PROJECT
Predictive modelling request for ALL CASE count
Activity
Activity
Work Force: Develop and maintain work force for epidemic response
Hiring for permanent positions
Health/Work balance practices
Communication: improve communciation of data, findings, and activities for public, state and local response partners
Improve useability of surveillance data
|  | Activity | Coordinate posting of statistics on website
|  | Activity | Explore availability of Tableau Server
Keep administration informed of activities, recommendations and needs
|  | Activity | Situation report on Epidemiology activities to higher administration
Improve communication with local public health
|  | Activity | Agile meeting
|  | Activity | Updated needed for regional epidemiologists
Provide better communication to/for/among staff working on epidemiology activities
Coordination: Project management
Coordinate data outputs
| Outputs | Activity | Research dua and data set distribution
| Outputs | Activity | Daily data distribution | Michael Jacobson/Samantha Crisci