State Prioritization Plan

COVIC-19 Diagnostic Testing strategy for June-August 2020

Revision Date: 05/27/20

Goal: Conduct 30,000 diagnostic tests for COVID-19 in the state to contain epidemic spread by focusing on highest priority vulnerable population in conjunction with local health departments, utilizing MDHHS Public Health Testing Criteria.

Plan in two-week increments for use of 3,030 tests per day per million people in each jurisdiction. Using planning module, MDHHS collaborate with LHD to prioritize populations and locations in their jurisdictions in two-week increments, prioritizing:

- Congregate care living facilities

  - Intake testing supplies for two weeks

  - Congregate care facilities in community each week

    - prioritize those with at least one facility associated case

    - prioritize those within facility most likely to have exposure

- Jails and homeless shelters at intake

  - Intake testing supplies for two weeks

  - One half of facilities in community each week

    - prioritize those with at least one facility associated case

    - prioritize those within facility most likely to have exposure

- High risk industries in your community every two weeks (meat packing, poultry, agriculture)

  - Prioritize facilities with known outbreaks or share staff with outbreak facilities

- Pop up locations and estimates for areas of low testing and social vulnerability

Roles

- MDHHS provide data, technical assistance and coordination with contractor.

- DTMB/SEOC with MDHHS BOL provide testing supplies.

- Local health departments identify specific locations and work with partners to promote testing and overcome barriers.

- MING or contractor will deliver sampling kits for facilities with medical personnel (ex. Jails, long term care, federally qualified health clinics).  Later in schedule: LHD to order materials to be mailed to these facilities.

- MING or contractor will provide testing services through pop ups or drive ups.

- Contractor will maintain a swat capacity for testing in outbreak response as local health departments need.  This request will be sent by local health department through county emergency manager to SEOC for coordination.

Schedule

COB Friday May 29: MDHHS send out testing criteria, data for planning and testing plan module

June 4: LHD provide plan back to SOM and MING/Contractor by Thursday Week One

MING or Contractor review plan and work with local health department to address scheduling issues or test shortages.

June 8: Plan finalized by Monday Week Two and implement through June 20

June 17 (Wed): LHD plan for week June 21 – July 4

July 1: LHD plan for weeks July 6- July 19

July 15: LHD plan for weeks July 20-August 1

July 29: LHD plan for weeks August 2- August 15

August 12: LHD plan for weeks August 16-August 20

Appendix One:  DATA SOURCES

TABLE FROM MCKINSEY:  Population of each county = number of tests if 3030 tests per million people per day

TABLE FROM MCKINSEY/MDHHS:  Social vulnerability index map/zip code information

TABLE FROM MMAG:  Zip code level cumulative testing rates for each jurisdiction

Appendix Two:  LHD BiWeekly Testing Plan Template

| Local Health Department Name: |  |  | Example |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Date of Testing Plan: |  |  | 5/27/2020 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Duration of Testing Plan: |  |  | May 31-June 13 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contact Name: |  |  | John Doe |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Contact Number: |  |  | XXX-XXX-XXXX |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Total Sample Request |  |  | 235 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Column1 | Type of site | Name of site |  | Address |  |  | Site Contact Name | Phone Number |  |  |  | Staff Needed for Sampling |  | Samples expected for period |  |  | Dates Preferred |  |  | Special Considerations |  |  |  |
| 1 | Homeless Shelter | Haven House |  | 333 Michigan Ave, Lansing MI |  |  | John Doe | xxx-xxx-xxxx |  |  |  | Yes |  | 5 |  |  | Daily at intake |  |  | Rapid test preferred for answer to be available to resident, will need physicians order |  |  |  |
| 2 | Homeless Shelter | Haven House |  | 333 Michigan Ave, Lansing MI |  |  | John Doe | xxx-xxx-xxxx |  |  |  | Yes |  | 25 |  |  | Monday, 5-10 pm |  |  | Testing all residents and staff |  |  |  |
| 3 | LTC | Easy Care LTC |  | 115 Grand Ave, Okemos, MI |  |  | Sally Door | xxx-xxx-xxxx |  |  |  | No |  | 45 |  |  | June 8th |  |  | Testing all residents |  |  |  |
| 4 | Pop Up | Pine Street Park |  | Pine Street, Lansing |  |  | Joe Mitchell | xxx-xxx-xxxx |  |  |  | Yes |  | 10 |  |  | June 6th |  |  | Coordinate with Syringe Service Program |  |  |  |
| 5 | LTC | Joes Old Age Home |  | 14532 M-37, Lainsburg, MI |  |  | Mia Callo | xxx-xxx-xxxx |  |  |  | Yes |  | 150 |  |  | Week of June 1 |  |  | Testing all residents, no medical personnel on staff |  |  |  |
| 6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Appendix Three:  Considerations for Pop up sites

Local Health Role for Pop Up Sites

- Identify test site and make contact with the owner for use of property, if available use of restrooms for staff and National Guard (may need porta potty rentals)

- Medical Director signature to order test

- Getting test kits to the lab (carrier) or drop off point

- Provide staff to process paperwork, registration and lab forms

- Obtain Tables, chairs and if needed pop up tents

- Provide Snacks and water for staff

- Provide PPE for health department staff

- Provide BIO Hazzard Trash Bags and Regular Trash Bags

APPENDIX FOUR: Considerations for Long Term Care Facility Testing

As you are aware, the National Guard/MSP completed testing of LTC facilities in the U.P. and downstate Phases I-VI.  Scheduling for the next phases of testing will begin for the counties Montcalm, Lapeer, Shiawassee, Isabella, Tuscola, Huron, Newaygo, Hillsdale, Barry, Alpena, and Allegan next week. The goal is also to return to Saginaw, which was missed due to the impact of the floods end of last week. Please note this is a head’s up – we are awaiting news that the required test kits will be available to cover all requests.

The Governor’s Office and MDHHS has requested the MSP and National Guard to ensure coordination with Health Officers for testing.  The Regional Michigan State Police Coordinator from your area will soon be in contact to discuss scheduling. The National Guard/MSP teams are aware that you all may have already began testing of LTC facilities. I know you have been asked to identify and prioritize facilities in your area where testing should be completed. The National Guard teams will follow your direction in regards to where testing should be done.

In the near future, you will be receiving an Outlook meeting invitation from MSP Captain Sweeney who is in charge of the overall operation.  Captain Sweeney is arranging a conference call (30 minutes) with the MSP coordinator in your area, along with the national guard and your health departments.  The calls will be scheduled for Thursday 9:30 a.m. May 28th and Friday 10:30, May 29th.  Counties will be split into 4 phases numbered 7-10 (see below for the phase of your county and the date and time of the scheduled call).

The teams will only test LTC facilities that are either tier 1 or 2, meaning they will not conduct testing in other congregate facilities.

Orders for the test are under the facility’s medical director where possible and testing is voluntary.

By the time of the call, The Team is requesting from each of your health departments the following:

- The list of long term care facilities (including address) that will be tested

- LHD to make phone calls to the identified facilities to let them know the National Guard will be on site for testing

- Number of test kits needed for each facility (testing includes residents and employees)

- Identify facilities that will need assistance with testing or that facilities will conduct their own testing

- Plan for how the test will get to the identified labs after testing is completed

Lab Capacity

The team would like to know if you have a relationship with a lab for testing, if not we can make arrangements with the state lab.

Appendix Five: Collection material examples

INSERT MUSKEGON CONSENT FOR TESTING UNDER STANDING ORDER OF PUBLIC HEALTH

INSERT MUSKEGON COVID 19 STANDING PUBLIC HEALTH ORDER

INSERT MUSKEGON COVID 19 TESTING REMINDERS FOR PARTICIPANTS